## Blizzards
Blizzards Statement of Work
| Project Title |  | Start Date
| Study Buddies |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Alina (Designer), Lonzo (Tester), Robin (Lead), Samuel (SWE) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Alina |  |  | 2025-11-22 | 2025-12-08 | 17 |  | Not Started
| # Create profile display, schedule input, and schedule display designs | Complete | SHA 1601da9, 4ef802, 3d45638 | 2025-11-22 | 2025-12-08 | 17 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
| # Create a Profile class that has attributes: id (int), first name(str), last name(str), schedule (list (Event)), major (str). Create a constructor and a _str_ method. The first and last names must be formatted in Titlecase. The major must be formatted in TITLECASE. The schedule must begin as an empty list. | Complete | 5a4d6cc, 03781c7 | 2025-11-24 | 2025-11-24 |  | #User Story 59 | Complete
| # Write separate unit tests to test: (1) the profile has an id, first name, last name, major, (2) the update schedule method updates the schedule, (3) that all the DateTimes are valid, (4) the major is either CS, CIS, CE, or BINF, and (5) the first and last names use Titlecase. | Complete | 19d938d, 2f15b69 | 2025-11-25 | 2025-11-27 |  | #User Story 59 | On Hold
| #Create an invite method that given two Profile objects, adds this study session to both profiles if the given DateTime is not already in both Profile objects' schedule. | Complete | 7c58b32, 821c1d6, 83bff45 | 2025-11-27 | 2025-11-27 |  | #User Story 60
| #Test that the str method displays using the format "Friday, Nov 21, 2025 at 11:28 PM has a study session on 'How to write use cases'". | Complete | 6a1cb45 | 2025-11-26 | 2025-11-26 |  | #User Story 60
| #Create a driver that generates 30 random StudySession objects, creates 2 Profile objects, stores 10 study sessions in the first profile, 10 study session in the second profile, and then invites both profiles to the final 10 study sessions. | Complete | 488aa88, 0b4654a | 2025-11-27 | 2025-11-27 |  | #User Story 60
| #Create an add_event method that adds an event to the student's schedule. Don't add if the event is already in the student's schedule or the student already has something scheduled at that DateTime. | Complete | 95ada72 | 2025-11-26 | 2025-11-26 |  | #User Story 62
| #Create a sort events method that sorts the events in a given Profile object. Sort the events in reverse chronological order. | Complete | 1a225ee | 2025-11-29 | 2025-11-29 |  | #User Story 62
| #Create tests for sort_evens method | Complete | 8ad16e3 | 2025-11-29 | 2025-11-29 |  | #User Story 62 |  | Nov 26th: 6 commits, +91, -10
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Lonzo |  |  | 2025-11-17 | 2025-12-08 | 22
| # Add pytest unit tests for Profile, Schedule, Session, Flashcards, etc. | On Hold | SHA 45ab501, fe680ac | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 29 commits, +483, -163
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Robin |  |  | 2025-11-22 | 2025-12-08 | 17
| # Update README with 6 numbered, prioritized projects | On Hold | SHA 0228979, 837cc5e | 2025-11-25 | 2025-11-25 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 36 commits, +337, -250
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Samuel |  |  | 2025-11-17 | 2025-12-08 | 22
| # create AutoCancelJob, FlashcardGenerator, InviteLogic, Profile, StudySession classes | On Hold | SHA d926e23, 10b580f | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 30 commits, +461, -122
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL