## Blizzards
Blizzards Statement of Work
| Project Title |  | Start Date
| Study Buddies |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Alina (Designer), Lonzo (Tester), Robin (Lead), Samuel (SWE) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments
| Alina (@apaiz12, apaiz@xula.edu) |  |  | 2025-11-22 | 2025-12-08 | 17
Profile(__init__, update_schedule), test_profile_attributes(), test_update_schedule(), test_valid_datetime_in_event(), test_invalid_major_raises_value_error(), test_name_titlecase() | #59 Create a Profile class that has attributes: id (int), first name(str), last name(str), schedule (list (Event)), major (str). Create a constructor and a _str_ method. The first and last names must be formatted in Titlecase. The major must be formatted in TITLECASE. The schedule must begin as an empty list. Write separate unit tests to test: (1) the profile has an id, first name, last name, major, (2) the update schedule method updates the schedule, (3) that all the DateTimes are valid, (4) the major is either CS, CIS, CE, or BINF, and (5) the first and last names use Titlecase. | Complete | 5a4d6cc, 03781c7, 19d938d, 2f15b69 | 2025-11-24 | 2025-11-27 | 4
invite(), has_conflict(), test_str_method(), generate_study_sessions(), and call | #60 Create an invite method that given two Profile objects, adds this study session to both profiles if the given DateTime is not already in both Profile objects' schedule. Test that the str method displays using the format "Friday, Nov 21, 2025 at 11:28 PM has a study session on 'How to write use cases'". Create a driver that generates 30 random StudySession objects, creates 2 Profile objects, stores 10 study sessions in the first profile, 10 study session in the second profile, and then invites both profiles to the final 10 study sessions. | Complete | 7c58b32, 821c1d6, 83bff45, 6a1cb45, 488aa88, 0b4654a | 2025-11-26 | 2025-11-27 | 2
add_event(), sort_events(), get_datetime() test_sort_events_basic(), test_sort_events_with_study_session() | #62 Create an add_event method that adds an event to the student's schedule. Don't add if the event is already in the student's schedule or the student already has something scheduled at that DateTime. Create a sort events method that sorts the events in a given Profile object. Sort the events in reverse chronological order. Create tests for sort_evens method | Complete | 95ada72, 1a225ee, 8ad16e3 | 2025-11-26 | 2025-11-29 | 4 | #User Story 62
ProfileDisplay.png, ScheduleDisplay.png | Create profile display, schedule input, and schedule display designs | Complete | SHA 1601da9, 4ef802, 3d45638 | 2025-11-22 | 2025-12-08 | 17 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Lonzo (@lonzojr7, lhamilt3@xula.edu) |  |  | 2025-11-17 | 2025-12-08 | 22
test_profile_creation(), test_schedule_updates_persist(), test_session_proposal_stores_details(), test_decline_invitation(), test_pending_session_auto_cancel_after_hours(), test_cancellation_notifications_sent(), test_flashcards_generate_for_correct_date_range() | #43-48 Add unit tests for Profile, Schedule, Session, Flashcards, etc. | Complete | SHA 45ab501, fe680ac, d8c0295 | 2025-11-17 | 2025-11-24 | 8
update_schedule_dict(), update_schedule(), change_major(), has_duplicate_events(), __repr__() test_update_schedule_single_event(), test_update_schedule_duplicate_dattie_prevented(), test_change_major(), test_no_duplicate_events() | #59 Add User Story #59 Uses Cases to user_profile.py. Test User Story #59 Use Cases | Complete | 2a6d62d, 9d5b2d7 | 2025-11-24 | 2025-11-24 | 1
remove(), check_duplicate_datetime(), add_to_frofile() test_remove_session_form_both_profiles(), test_no_duplicate_datetime() | #60 Create a remove method. Create two methods that help each other check for duplicate datetimes. Test Study Session Use Cases. | Complete | 420dc3b, 0c0d40f, f9bcd07 | 2025-11-24 | 2025-11-24 | 1
remove_event(), output_events() test_remove_event(), test_output_events() | #62 Create a remove_event method. Create an output_events method. Add remove_event method from User Story #62 into user_profile.py file. Add output_events method from user story #62 to user_profile.py file. Add test_remove_event method in test_user_profile.py file. Add test_output_events method to test_user_profile.py file. | Complete | 476de6c, d774f0c, 7326a0e, 9f7e340, 2671261, 092c23e, b9fcc724b87345697f502f8ba7, 28aaca0 | 2025-11-24 | 2025-11-24 | 1
sort_study_sessions(), upcoming_study_sessions() test_study_sessions(), test_upcoming_sessions(), test_sort_empty_schedule() | #75 Create a Sort Study Sessions function from earliest to latest. Create a function that filters only upcoming sessions. Test sort_study_sessions function. Test upcoming sessions function. Test for an empty schedule. | Complete | 0d9b462, 6bc4493, d3f41cc, f9519ad, 46a6746 | 2025-11-29 | 2025-11-29 | 1
count_availability_by_hour(), best_hour() test_sort_study_sessions(), test_upcoming_sessions(), test_best_hour_empty() | #76 Create Count Student Availability by Hour function in user_profile.py. Create a function that returns the hour with the highest availability. Test count_availability_by_hour method. Test best_hour method. Test if there is not a best hour. | Complete | 89379b9, aa3d348, ee2e7f8, 18707a1, 462c5cb | 2025-11-29 | 2025-11-29 | 1
has_conflict(), add_study_session() test_event_vs_event_conflict(), test_session_vs_session_conflict(), test_add_study_session_success(), test_add_study_session_fail_on_conflict() | #77 Create a function that checks for availability conflicts. Create a function that adds a study session only if it does not conflict with another. Test that all conflict types are identified. Test that a study session is added if there are no conflicts. Test that a study session is not added to the schedule if it conflicts with another. | Complete | e4a273b, dca2cbd, 20508d0, 54341123, a32360bbb890d11ad4da1235de83585b, 99abe78 | 2025-11-29 | 2025-11-29 | 1
| Add standup_meetings.txt File | Complete | 2c9b719 | 2025-11-20 | 2025-11-20 | 1 | This was done before we had our first user story.
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Create two __init__.py files | Complete | 36e78ff | 2025-11-24 | 2025-11-24 | 1 | This was done for testing reasons
| Update imports in test_study_buddies.py , invite_logic.py, auto_cancel.py, main.py, test_user_profile.py, test_event.py, file | Complete | 163174a, d7b3f9b, 4e24579, 0caaac7, e06a311, c6b7d7d | 2025-11-24 | 2025-11-24 | 1 | This was done to fix our team's coding structure
| Ran tests on test_study_buddies.py file | Complete | 4d316c1 | 2025-11-24 | 2025-11-24 | 1
| Remove use cases from event.py | Complete | 240e85d | 2025-11-24 | 2025-11-24 | 1 | This was done to fix our team's coding structure
| Remove Blizzards Modules from each .py file | Complete | 62cd261 | 2025-11-25 | 2025-11-25 | 1 | This was done to fix our team's coding structure
| Add important imports to user_profile.py & test_user_profile.py | Complete | 2941718, cd258198eb10feeecf3354565bbceb5b8 | 2025-11-29 | 2025-11-29 | 1 | This was done to fix our team's coding structure
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Robin (@justrobin14, rhall9@xula.edu) |  |  | 2025-11-22 | 2025-12-08 | 17
print_welcome_banner() and call | #63 Create a driver that has an ASCII art welcome message | Complete | SHA 56be12d2, 323162d, 9ba3910 | 2025-11-25 | 2025-11-25 | 1
generate_student_profiles(), find_longest_schedules() | #64 Update driver so it randomly creates 111 student profiles and then outputs the student(s) with the longest schedule | Complete | SHA ddd432a, e4bdef1, ad88e06, 692794b, 361fe18 | 2025-12-01 | 2025-12-01 | 1
edited main(), called invite() | #65 Update the driver to randomly create 222 study sessions and then randomly select any 2 profiles to study the same study sessions | Complete | SHA 9a0006e, bb3955c, 2a65b0c | 2025-11-25 | 2025-11-25 | 1
edited main(), called remove_two_session() | #66 Update the driver to randomly create 33 study sessions and successively remove those sessions from any 2 randomly selected profiles | Complete | SHA a32bb34, 1a25ea0, b5f81f1 | 2025-11-25 | 2025-11-25 | 1
| #78 As a developer, I want to identify and comment-out failing unit tests in the tests directory, so that the tests run to completion. | Complete | SHA 9e97b3f, 0ef341, 86b03dc | 2025-12-01 | 2025-12-01 | 1
| #79As a developer, I want to identify and comment-out any code in my driver that causes it to not print the start and end of the driver successfully to verify that the code can build and run in the CLI | Complete |  | 2025-12-01 | 2025-12-01 | 1
| #80 As a developer, I want to finish writing and organizing the Software Design Document (SDD), so that viewers of the repo have a reference for system architecture, class diagrams, workflows, and design decisions. | Complete |  | 2025-12-01 | 2025-12-01 | 1
README | Update README with 6 numbered, prioritized projects | Complete | SHA 0228979, 837cc5e | 2025-11-25 | 2025-11-25 | 1
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Samuel (@SMAX-byte, smaxey@xula.edu) |  |  | 2025-11-17 | 2025-12-08 | 22
| #59 Create smaxey_base branch | Completed | 10b580f | 2025-11-22 | 2025-11-23 | 1
| #62 Update Event class formatting | Completed | 8c81819 | 2025-11-22 | 2025-11-23 | 1
AutoCancelJob (__init__, auto_cancel, notify_buddies) | #59-60, 62-64 Merge smaxey_base to main with no conflicts | Completed | d926e23, 10b580f |  | 2025-11-29
extract_datetime(), _has_datetime_conflict() | #60 Update StudySession class | Completed | bdc4f75 | 2025-11-25 | 2025-11-26 | 1
| #69 Update user_profile.py | Completed | bdc4f75 | 2025-11-25 | 2025-11-28 | 3
update main(), mmp_driver() | #63 Add Study Buddy App Menu, Implement initial MMP driver logic | Completed | 3920b64, a0e2d64 | 2025-11-26 | 2025-11-28 | 1
test_longest_schedule(), test_create_30_profiles | #64Test mmp_driver.py | Completed | cbbe4db | 2025-11-27 | 2025-11-29 | 2
| #60-63 Sync Blizzards branch with upstream | Completed | d130e29 | 2025-11-30 | 2025-11-28 | 2
random_name(), random_major(), random_datetime(), random_event(), random_study_session(), random_111_profiles(), create_30_profiles(), remove_33_sessions(), run_task_65(), run_mmp_driver() | #66 Finish MMP driver | Complete | 34a0610 | 2025-12-01 | 2025-11-30 | 1
See Row 46 | create AutoCancelJob, FlashcardGenerator, InviteLogic, Profile, StudySession classes | Complete | SHA d926e23, 10b580f | 2025-11-17 | 2025-11-17 | 1
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 3
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F14)
End Date = MAX([End Date, row below]:G14)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL