## Blizzards
Blizzards Statement of Work
| Project Title |  | Start Date
| Study Buddies |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Alina (Designer), Lonzo (Tester), Robin (Lead), Samuel (SWE) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Alina |  |  | 2025-11-22 | 2025-12-08 | 17 |  | Not Started
| # Create profile display, schedule input, and schedule display designs | On Hold | SHA 1601da9, 4ef802, 3d45638 | 2025-11-22 | 2025-12-08 | 17 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
Complete
On Hold
Nov 26th: 6 commits, +91, -10
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Lonzo |  |  | 2025-11-17 | 2025-12-08 | 22
| # Add pytest unit tests for Profile, Schedule, Session, Flashcards, etc. | On Hold | SHA 45ab501, fe680ac | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 29 commits, +483, -163
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Robin |  |  | 2025-11-22 | 2025-12-08 | 17
| # Update README with 6 numbered, prioritized projects | On Hold | SHA 0228979, 837cc5e | 2025-11-25 | 2025-11-25 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 36 commits, +337, -250
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Samuel |  |  | 2025-11-17 | 2025-12-08 | 22
| # create AutoCancelJob, FlashcardGenerator, InviteLogic, Profile, StudySession classes | Complete | SHA d926e23, 10b580f | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
| #Finish MMP driver | Complete | 34a0610 | 2025-12-01 | 2025-11-30 | 1 | 66
| #Merge smaxey_base to main with no conflicts | Completed | d926e23, 10b580f |  | 2025-11-29 |  | 59, 60, 62, 63, 64
| #Sync Blizzards branch with upstream | Completed | d130e29 | 2025-11-30 | 2025-11-28 | 2 | 60–63
| #Add Study Buddy App Menu | Completed | 3920b64 | 2025-11-27 | 2025-11-28 | 1 | 63
| #Test mmp_driver.py | Completed | cbbe4db | 2025-11-27 | 2025-11-29 | 2 | 64
| #Implement initial MMP driver logic | Completed | a0e2d64 | 2025-11-26 | 2025-11-27 | 1 | 63
| #Update StudySession class | Completed | bdc4f75 | 2025-11-25 | 2025-11-26 | 1 | 60
| #Update user_profile.py | Completed | bdc4f75 | 2025-11-25 | 2025-11-28 | 3 | 69 |  | Nov 26th: 30 commits, +461, -122
| #Create smaxey_base branch | Completed | 10b580f | 2025-11-22 | 2025-11-23 | 1 | 59
| Update Event class formatting | Completed | 8c81819 | 2025-11-22 | 2025-11-23 | 1 | 62
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL